## Slide 1
WaferEngine · CS-3
WEEKLY UPDATE
KV reuse inside one card now works end to end
S6 closes M0's reuse line. M1 opens on holding several requests at once.
OWNER
Le Xu
PERIOD
20 - 26 July 2026
FOCUS
M0 closes Line 1, M1 opens
Notes: Last week's deck covered S6a on real silicon. This week: force-decode lands, S6 closes, and M1 is planned.

## Slide 2
ROADMAP
Where we are
DONE
M0, Line 1
PE-internal KV reuse: retain and force-decode
PARKED
M0, Line 2
KV transport, waiting on the cluster
NOW
M1
Several requests resident in one card
NEXT
M2
Reuse architecture, settled by benchmark
LATER
M3 - M6
Idle-PE tier, off-chip pool, policy, scenarios
Notes: M0's transport half stays blocked on the CS-3 cluster being down; M1 runs in simulation and does not wait for it.

## Slide 3
PROGRESS
Since last week
Force-decode (S6b) was designed, built in three stages and verified in simulation, then merged.
That closes S6, so M0's reuse line is complete: decode retain, prefill warm-start and force-decode all sit on one branch.
Two device sweeps finished on real silicon: prefill at a 16,384-token prompt and decode at a 4,096-token context.
M1's slot contract was reviewed and approved, and the first subtask is already built and verified in simulation.
Building it reversed two things the contract had assumed, so the design is now shaped by code rather than by argument.
M2 grew from a single cost model into a cluster of coupled architecture questions, each to be settled by a benchmark.
Notes: The two device sweeps completed on 21 July, one day after last week's deck. The two reversals: the device now gets one slot per lane rather than a single slot number, because eviction victims are not contiguous across lanes; and per-slot lengths stay on the host rather than being counted on the device.

## Slide 4
01
What now works
Three mechanisms, one branch.

## Slide 5
THE IDEA
Reuse what is already there, and force-decode only the new text
Force-decode runs ordinary decode steps, but the host supplies the token instead of the model sampling one, so the sampling work is skipped.
Notes: The key point: a second turn no longer has to re-read the first turn from token 0.

## Slide 6
CAPABILITY
What is supported today
Decode keeps its KV across rounds and extends it, rather than rewinding to zero. Correctness checked in simulation, cost measured on the wafer.
Prefill can start from a resident prefix instead of token 0, and its output is byte-identical to a cold run, both in simulation and on the wafer.
New text can be appended to a kept context by force-decoding it. Verified in simulation only so far.
Still one resident request per bank. Holding several at once is exactly what M1 adds.

## Slide 7
02
What we measured
Two sweeps on real silicon, one finding that changed our mind.

## Slide 8
PREFILL, REAL WSE-3
The reuse fraction dominates; length only nudges it
Time saved by starting from a resident prefix. 524,288 PEs, one run per point.
PREFIX REUSED
8,192-TOKEN PROMPT
16,384-TOKEN PROMPT
DIFFERENCE
none (cold)
1,001 ms
3,145 ms
baseline
25 %
-7.7 %
-7.3 %
-0.5
50 %
-22.8 %
-23.8 %
+1.1
75 %
-45.2 %
-49.8 %
+4.6
Notes: The 16,384 column completed this week. Every reuse round was byte-identical to the cold round. Saving is sub-linear because a reused prefix is always the cheapest part of the prompt: the last chunk costs about 7x the first.

## Slide 9
DECODE, REAL WSE-3
Retain wins by skipping whole steps
-49.3%
second decode round at a 4,096-token context, the point measured this week
-51.4%
Second round
1,024-token context
-34.6%
Both rounds together
1,024-token context
+0.02%
Equal-work control
a retained step is not cheaper
Notes: The control row is the point: when both arms run the same number of steps, retain is 0.02% slower. Its whole value is that steps already taken are not taken again. So the saving tracks the fraction of decode steps skipped, not the sequence length.

## Slide 10
HOW IT WORKS
Two reasons a forced step could be cheaper
A plain step cannot start until the one before it has picked its token. Supplying the token removes that stage, and removes the wait along with it.
Notes: The two effects cannot be switched on and off independently in the kernel: dropping the picking stage without also dropping the drain that feeds it unbalances the fabric and hangs. So they have to be told apart by the shape of the curve on the next slide.

## Slide 11
FORCE-DECODE, SIMULATOR
The line is straight, so it is skipped work, not overlap
Toy layout: 2x2 blocks, width 64, vocabulary 24. A forced step costs about 28% of a plain step here, roughly 806 cycles against 2,856.
Notes: Same configuration, pipelined against non-pipelined, was 17,149 to 13,096 cycles per token, a 24% saving. Correctness held at 9.8e-5 against the oracle.

## Slide 12
FINDING
This partly falsified what we expected
We expected the gain to come from layer pipelining: forced tokens let the front of the model run ahead and fill the pipeline.
A straight line rules that out. Pipelining would flatten once the pipeline is full; a constant saving per forced step means work is simply not being done.
Each forced step drops its sampling and output-projection stage, and that should grow with a real 128k vocabulary.
Still open: this layout has very little per-layer compute, so whether pipelining also helps at real scale is unmeasured.

## Slide 13
03
M1, and what to decide
Several requests in one card, and the architecture questions behind it.

## Slide 14
M1 CONTRACT
One number becomes two: capacity and compute
Slots size the cache, batch sizes the compute. The device is told one new thing, which slot each lane is on; everything else stays on the host.
Notes: Batch is a scheduling subset of the slots, not a storage axis. A slot-by-batch grid would over-allocate.

## Slide 15
M1 PLAN
Six subtasks, the first two now done
STEP
WHAT IT DELIVERS
STATUS
NOTE
S0
Slot addressing and metadata contract
done
Reviewed and approved, 26 July
S1
Multi-slot cache, inert
done
Bit-identical on both gates, in simulation
S2
Retain and extend across a changing active set
on track
Next: per-slot lengths on the host
S3
Hit detection, eviction, miss handling
planned
A miss rebuilds by force-decoding
S4
Requests-per-bank capacity curve
planned
Needs a geometry near the SRAM budget
S5
End-to-end verification
planned
Against a teacher-forced reference
Notes: S1 passed two gates in simulation: bit-identical to the pre-change build over 48 records, and bit-identical again with four slots and the active set mapped to slots 3 and 0, with the unused slots still exactly zero. Capacity is not exercised at this geometry. The code is still uncommitted in the working tree.

## Slide 16
TO DISCUSS
The M2 questions
WHY TOGETHER
One architecture, not four separate calls
These choices constrain each other. Paging's page table is exactly the per-PE mapping a distributed control plane would need, so picking one nearly picks the other. M1 commits to the simplest working defaults, fixed slots with control on the host and the cache in decode, and M2 tests each against a small benchmark rather than settling it by argument.
FOUR COUPLED QUESTIONS
01
Does the control plane live on the host, or distributed across the compute PEs?
02
Fixed-size slots, or paging for copy-free prefix sharing?
03
On a hit, continue in decode, or ship the KV back to prefill?
04
Does the cache live in decode or in prefill?
Notes: Paging would chop the attention inner loop into roughly 16 short pieces at 256 tokens and 16-token pages, which is why M1 does not start there.

## Slide 17
ALSO TO DISCUSS
Open routing calls
Continuous batching: M1 builds the substrate, but running requests concurrently needs ingress, egress and a scheduler reworked. Which milestone owns it?
Ragged batch, meaning lanes sitting at different sequence positions. M1 declined it, but continuous batching needs it. Do we cost it on its own?
Do we run the control-plane comparison inside M1, or on a branch forked after M1-S2?
Measuring real-scale pipelining needs a compute-heavy configuration. Is it worth the wafer time?
The CS-3 cluster is down, so M0's transport work stays parked. M1 runs in simulation meanwhile.

## Slide 18
NEXT STEPS
What happens next
Le Xu
Commit the S1 working tree, which is the one thing holding up S2.
Le Xu
Build S2: per-slot lengths on the host, across a changing active set.
Team
Decide which of the M2 questions gets a benchmark first.

## Slide 19
WaferEngine · CS-3
Questions?
Plan in ROADMAP.md, current state in PROGRESS.md, detail in milestones/M1-intra-pe-reuse.md.
lxu5398@gmail.com